## Slide 1
Work Package 5
The way forward
Utrecht 17th January 2014
Timeline for the High Resolution study
Jan Maarten van der Zwan

## Slide 2
Start data collection
Data collection completed
Timeline
Run data check exercise
Feedback data check exercise
Final data analyses
January
April
May
June
August
Final Report for EU
Presentation final results
October
Notes: I expect WP 1 to present the general aim of the project

## Slide 3
Start Data collection
Discussion data collection protocol
Revision of the protocol and data collection tool
Ask permission data protection boards
Collect data following protocol
Send in collected data
Help Desk for questions (j.vanderzwan@iknl.nl)
Notes: I expect WP 1 to present the general aim of the project

## Slide 4
Data collection completed
Send in the dataset to: j.vanderzwan@iknl.nl
Encrypt the database by using:
    WinZip
    WinRAR
    Password*: Country and Capital
    (small letters only)
    Example: netherlandamsterdam
*This password will be used for further exchange of data
Notes: I expect WP 1 to present the general aim of the project

## Slide 5
Run data check
Data collection completed
Data check upon:
  Completeness of the data
  Strange combinations topo / morpho codes
  Rarities for TNM and staging
  Ask expert opinion
    Clinicians
    CR experts
Notes: I expect WP 1 to present the general aim of the project

## Slide 6
Feedback data check
Cancer Registries will be informed with the results of the data check
Cancer Registries correct their data or motivate the results
There is an agreement on the final data set
Notes: I expect WP 1 to present the general aim of the project

## Slide 7
Final data analyses
The data will be analysed for presentation
  Per country/region
  EU overall
  Per indicator
Additional analyses in case possible
Notes: I expect WP 1 to present the general aim of the project

## Slide 8
Final results
The outcome will be presented to the participating Cancer Registries
The outcome will be presented to the collaborating partners
Final report to the European Commission
Scientific publication in case of approval from the participating Cancer Registries
Notes: I expect WP 1 to present the general aim of the project

## Slide 9
Finance
At the moment we are working on an amendment for shifting money within our Work Package to contribute to the data collection.
In case the amendment is approved we can support each country with:
€2000,-*
* This will be transferred to your cancer registry after submitting your data for analyses
Notes: I expect WP 1 to present the general aim of the project

## Slide 10: Questions and suggestions