## Slide 1
Work Package 5
Information on centres of expertise for rare cancers
WP leader: Sabine Siesling

## Slide 2: Work Package 5
Aim
      To identify the qualification criteria for centres Centres of Expertise (CoE) for rare cancers
Deliverable (No: 7)
  Report identifying criteria indicating the level/quality of expertise for rare cancers management
Notes: <number>
I expect WP 1 to present the general aim of the project

## Slide 3: How?

## Slide 4: How?
with a wide consensus process and high resolution studies and feedback/discussion on the results
Together with partners, collaborators, clinicians, patients, scientific societies, health authorities

## Slide 5: Partners WP5
      Associated partner:
INT, ISS, UEDIN, ECPC, NOH, NCR, CSF, OILJ
    Collaborating partners:
  RCE (Rare cancers Europe), EPAAC, ESSO, ESO, INSERM (Orphanet), Centre of Leon Bernard, ESMO, LeukaNet, ECCO
  To be determined: experts for selected tumour types!
Notes: <number>
Question: ECPC was mentioned as associated partner: that is not in the final proposal! RCE was mentioned in the colaborating partners, this was not mentioned in the proposal
These are the partners involved for our WP, explain their possible contribution

## Slide 6: Milestones
Milestones
    Consensus meeting on criteria CoE
    A protocol for the high resolution study
    Data collection and analysis
    Meeting to discuss the results
    Final dissemination meeting with experts held/report
Notes: <number>
I expect WP 1 to present the general aim of the project,

## Slide 7: General criteria
General criteria for CoE on all rare diseases available
  European Union Committee of Experts of rare diseases (EUCERD)
  Multidisciplinary scientific society
  Patient organizations
  Policy makers
Notes: <number>

## Slide 8: Possible general criteria (EUCERD):
1) the attractiveness measured through the volume of cases treated (link to WP4),
2) the capacity to produce and adhere to clinical guidelines (i.e. staging procedure and treatment),
3) outcomes (i.e. surgical free margins, number of revision surgery, survival and recurrence),
Notes: 2) Is basis for tumour specific indicators
<number>

## Slide 9: Possible general criteria (EUCERD):
4) the availability of multidisciplinary team,
5) the collaboration with other centers of expertise at national and international level (also for clinical trials).
6) capacity to participate in data collection (clinical research and public health in relation to CR)

## Slide 10: Specific criteria/indicators criteria for expert groups
Develop tumour specific indicators for CoE on specific rare tumours preferably based on guidelines
All experts involved in diagnostics and treatment for specific tumour
Pathology, medical oncology, surgery, radiotherapy, patient advocacy groups
Notes: <number>
These are the steps in global to make to come to the results

## Slide 11: Specific criteria/indicators
Develop tumour specific indicators for CoE on specific rare tumours preferably based on guidelines
> discussion on level of detail
Based on patient pathway
  Diagnosis
  Treatment
  Follow-up
Notes: <number>
These are the steps in global to make to come to the results

## Slide 12: Define criteria for the indicators
Valid
Reliable
Reveal differences
Describe either structure (challenge to collect), process or outcome
Influences outcome of the patient (difference in indicator matter)
Registration by CR

## Slide 13: Specific criteria/indicators examples
Diagnosis:
  Use of imaging/specific diagnostics
  Stage at time of diagnosis
  Pathology report (reviewed)
  Pre-treatment MDT
  Availability of relevant disciplines at MDT (pathologist etc)
  time between pathological confirmation and first treatment
Notes: <number>
These are the steps in global to make to come to the results

## Slide 14: Specific criteria/indicators examples
Treatment:
  Referral pattern = hospital of diagnosis and hospital of treatment
  According to guideline
  Free margins after surgery/number of revisions
  Post-treatment MDT
  Availability of different disciplines at MDT (pathologist etc)
  time between first treatment and adjuvant therapy
Notes: <number>
These are the steps in global to make to come to the results

## Slide 15: Specific criteria/indicators examples
Follow-up:
  1, 3, 5 year survival (WP4)
  Recurrence within 5 years after diagnosis
  Patient satisfaction (not collected by CR!)
  Information to patient about treatment
General:
  Organisation of care: a case manager for every patient (too much detail, survey? Not by data from CR)
Notes: <number>
These are the steps in global to make to come to the results

## Slide 16: Specific criteria/indicators plan of action
Check availablility in EU Cancer Registries (CR)
Some CR will be invited to collect information from clinical files in retrospect (time period important for ability to find data (electronically), partly overlap of period of Wp4)
Develop a protocol to retrieve data for these High Resolution Studies
Notes: <number>
These are the steps in global to make to come to the results

## Slide 17: High Resolution Studies
Collect data on specific indicators by high resolution study using a set protocol
Selected number of CR (partners NL, Finland, Italy, Ireland, Bulgaria, Slovenia i.e. based on EUROCHIP survey on availablity stage etc)
Analyse data
Discuss results with experts
Describe an advice upon CoE for the specific rare cancers
Notes: <number>
Cont.

## Slide 18: Criteria for Selection of rare cancer types
Which rare cancers to select for High Resolution Study?
Rationale:
Expected difference in clinical management (adherence to guidelines)
Expected difference in clinical outcome
Take geographical patterns and trends in incidence into account (mesothelioma, Thyroid cancer): WP4!
Already work done by other groups (could be included in expert groups)
Notes: <number>

## Slide 19: Proposal for High Resolution Studies
Five (?) groups of rare tumours we could focus on;
  Mesothelioma (Italy, NL, clusters)
  Sarcomas (EPAAC)
  Leukemia (partner)
  Endocrine tumours (thyroid cluster?, Finland)
  Neuroendocrine tumours
Notes: <number>

## Slide 20: Timeline
M2: Kick off meeting (Now)
M3: Start preparing consensus meeting with experts
M7: Start developing protocol
M8: Consensus meeting with experts
M9: Send out protocol for data on indicators
M9-M17: Collect data from CR
M17-M19: Data analyses
M21: Data collection and data analyses completed
M23: Meeting to discuss output with CR
M24: Meeting present results to experts
Notes: <number>
In reallity this is the strategy linked to a timeline. This is important for WP4 to check as the changes we made will affect their timeline

## Slide 21: Expected results and output
Notes: <number>
This is the final deliverable, the report will be written in a way that it can be used by WP7

## Slide 22: Link to other WP’s
Notes: <number>
Appoint chortly the relation between our WP and the others.
WP 3 is the only exeption, we are not in direct contact with this WP.
This overview is not representing the relation between other WP, this should maybe be clarified
Relation wp1: We inform them on all our activities, we get feedback from their site.
wp2: We will give input towards dessimination plan , this is a relative one way process
wp3: No direct contact, contact will be via WP1
wp4: Close collaboration, we need each others’ information to come to the expected results
wp6: They will develop a gateway for information, we have to give input upon their request
wp7: Close collaboration, our WP will give them input to loby and indicate on CoE.

## Slide 23: Questions and suggestions
Notes: <number>

## Slide 24
Notes: <number>
Ik denk dat de introductie een korte uitleg kan geven over onze organisatie en de mogelijk de recente fusie.
Daarna een toelichting van de EU projecten waar we bij betrokken zijn en wat we daarin doen/gedaan hebben.
Daarnaast is het denk ik belangrijk aan te geven hoe we betrokken waren bij het RARECARE project
Uiteindelijk kunnen we hier uitleggen waarom IKNL de partner is om bij RARECARENet te betrekken

## Slide 25: Introduction
Notes: <number>
A short introduction upon our organisation and the role of it within the EU.
shortly explain how we were involved for this project (explaining EUROCHIP and RARECARE)

## Slide 26: Content: ADAPT!!!
Aim of Work Package 5
Milestones
Methodology
Timeline
Example
Expected results and output
Link to other Work Packages
Notes: <number>

## Slide 27: Strategy: Example
Identify the common indicators on rare disease (example: EUCERD indicators)
  Identify existing indicators and criteria on specific tumour
  Discuss criteria with experts and find consensus
Develop protocol
on data collection Collect data and analyse
for the criteria data for the experts
Notes: <number>
As requested we give a example on how to work (process) for in this case NETs, this to better explain and visualise our plans to come to the results using the mile stones